## CIP
SUMMARY OF MAJOR ROAD PROJECTS PROGRAMMED BY LEE COUNTY - FY23/24-27/28
FY 98-22
COMM | PROJ. |  |  | PRIOR | 22/23 | [5 empty] | 5-YEAR |  | PROJECT | REVENUE | PROJECT
DIST. | # | PROJECT NAME | DRIVER | EXP. | BUDGET | 23/24 | 24/25 | 25/26 | 26/27 | 27/28 | TOTAL | 6-10 | TOTAL | SOURCE | MANAGER
MAJOR PROJECTS
2,5 | 209245 | Alico Rd. Connector/Alico Rd. to SR 82 opposite Sunshine Blvd. | People-to-jobs link, | 5865862 | 20125037 | 4547555 | 13000000 | 55682342 | 0 | 92000000 | 165229897 | 39272804 | 230493600 | IF 23, 25 | Vince Miller
|  | Extension of Alico Rd through SR 82 and including widening of Sunshine Blvd | Daniels Pkwy. relief | ROW | ROW/DES |  |  | DES/CST | [5 empty] | GT | vmiller@leegov.com
|  | constructed in two phases | NM - Core Critical | [10 empty] | ST
All | 206002 | Bicycle/Pedestrian Facilities | Implementation of bike- | 23377364 | 8793098 | 2003160 | 6570350 | 2694834 | 11363460 | 1490864 | 24122668 |  | 56293130 | IF/GT | Tom Marquardt
|  | Annual project for facilities on existing County-maintained roads | ped plan, BPAC prior- | [11 empty] | tmarquardt@leegov.com
ities, Complete Streets
|  | Specific Projects: | principals
1 |  | Hancock Bridge Pkwy Orange Grove - 4055 Hancock | 2016 Priority #22 |  |  | 495000 | 0 | 546250 | 0 | 0 | 1041250 |  | 1041250 | IF22
[6 empty] | DES/SUR |  | CST/CEI
1 |  | Barrett Rd Pondella - 3400N of Pondella | 2016 Priority #23 |  |  | 0 | 225537 | 0 | 1296842 | 0 | 1522379 |  | 1522379 | IF22
[7 empty] | DES/SUR |  | CST/CEI
|  | North Key Dr Beau Dr to US 41 | 2017 Priority #4 |  |  | 0 | 45536 | 0 | 252664 | 0 | 298200 |  | 298200 | IF22
[7 empty] | DES/SUR |  | CST/CEI
|  | Plantation Daniels -Idlewild | 2020 Priority #13 |  |  | 1369367 | 0 | 0 | 6846833 |  | 8216200 |  | 8216200 | GT
[6 empty] | DES/SUR |  |  | CST/CEI
|  | Orange River Blvd Palm Beach Blvd - Loraine Dr | 2019 Priority #2 |  |  | 0 | 0 | 2268782 | 0 | 0 | 2268782 |  | 2268782 | GT
CST/CEI
5 |  | Bell Blvd SR 82 - Sunrise | 2016 Priority #4 |  |  | 0 | 3557183 | 0 | 0 | 0 | 3557183 |  | 3557183 | GT
CST/CEI
5 |  | Westgate Blvd East Lee - 4th | 2015 Priority #2 |  |  | 0 | 0 | 0 | 128139 | 0 | 128139 | 736799 | 864938 | IF23
[9 empty] | DES/SUR |  |  | CST/CEI
5 |  | Westgate Blvd West 4th - Lee | 2016 Priority #3 |  |  | 0 | 0 | 0 | 117436 | 0 | 117436 | 675257 | 792693 | IF 23
[7 empty] | 0 |  | DES/SUR |  |  | CST/CEI
|  | Westgate N Lee-Sunshine | 2017 Priority #2 |  |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 | IF23
[9 empty] | DES/SUR |  |  | CST/CEI
|  | Westgate S Lee-Sunshine | 2017 Priority #3 |  |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 | IF23
[9 empty] | DES/SUR |  |  | CST/CEI
|  | Alico RR Crossing - Quaker | 2016 Priority #3 |  |  | 0 | 0 | 1091247 | 0 | 0 | 1091247 |  | 1091247 | IF 25
CST/CEI
|  | Pine Rd Allaire - US 41 | 2020 Priority #3 |  |  | 0 | 135801 | 0 | 780858 | 0 | 916659 |  | 916659 | IF 25
[7 empty] | DES/SUR |  | CST/CEI
2 |  | Jetport Loop Jetport Loop W - Commerce Loop | 2015 Priority #27 |  |  | 138793 | 0 | 798057 | 0 | 0 | 936850 |  | 936850 | IF25
[6 empty] | DES/SUR |  | CST/CEI | 0
4 |  | Pine Ridge Rd Summerline Rd - Kelly Rd | 2016 Priority #28 |  |  | 0 | 0 | 259280 | 0 | 1490864 | 1750144 |  | 1750144 | IF24
[8 empty] | DES/SUR |  | CST/CEI
|  | Pine Ridge Rd. Stevens-Summerlin | 2017 Priority #12 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | IF24
|  | Pine Ridge Rd San Carlos Blvd - Summerlin Rd | 2020 Priority #5 |  |  |  | 337511 | 0 | 1940688 | 0 | 2278199 |  | 2278199 | IF 24
[7 empty] | DES/SUR |  | CST/CEI
3 | 205724 | Big Carlos Pass Bridge | Age Condition of bridge | 6090725 | 97859141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103949866 | ST | Dave Murphy
|  | Replacement of Big Carlos Pass Bridge with a fixed span | (Bridge Health Index) | PD&E Study | CST/CEI | [8 empty] | DEBT | dmurphy@leegov.com
|  |  |  | DES | [9 empty] | GT
Mandated
1,2 | 209248 | Cape Coral Bridge Replacement | Age/condition, escalating | 1161114 | 18307104 | 0 | 0 | 0 | 224480000 | 0 | 224480000 |  | 243948218 | ST | Vince Miller
|  | Replacement of the EB and WB spans of the Cape Coral Bridge | maintenance costs | PD&E Study | PD&E Study |  |  |  | CST/CEI |  |  |  |  | Debt | vmiller@leegov.com
|  |  | Mandated | DES | DES
| 200769 | Midpoint Bridge | Concurrency, LOS | 0 | 15473314 | 0 | 0 | 0 | 0 | 0 | 0 | 279931305 | 295404619 | ST | TBD
|  | Widening of the Midpoint Bridge |  |  | PD&E Study | [8 empty] | Debt
DES
1,4 | 200669 | Corkscrew Road | Reduce congestion/wait | 16564044 | 38498960 | 4999575 | 0 | 0 |  | 0 | 4999575 | 0 | 60062579 | IF25 | Dave Murphy
|  | Widening of Crokscrew Rd from Ben Hill Griffin Pkwy to Bella Terra Blvd, constructed in | time, Improved safety | DES | ROW/DES/CST | CST | [7 empty] | Debt | dmurphy@leegov.com
|  | two phases | [11 empty] | GT
FDOT
CON
4 | 200671 | Gateway at Griffin Roundabout | Improve safety without | 470702 | 9133960 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9604662 | IF 23 | Dave Murphy
|  | Addition of a roundabout at Gateway Blvd and Griffin | adding delay | DES | DES/ROW | [8 empty] | GT | dmurphy@leegov.com
Debt
5 | 209246 | Gunnery Rd./8th St. Intersection Improvements | Intersection control |  | 1579817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1579817 | GT | Alex Slaibe
|  | Signalization and turn lane improvements | needed |  | DES/ROW | [8 empty] | FDOT | aslaibe@leegov.com
NM- Core Critical
5 | 205063 | Homestead 4L/Sunrise-Alabama | LOS, community interest | 13438332 | 9784294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23222626 | IF23/GT/ | Vince Miller, 533-8577
|  | 4L widening, south of Sunrise Blvd. to Alabama Rd., including on-road | Mandated | DES/ROW | DES/ROW/ | [8 empty] | GIF | vmiller@leegov.com
|  | bike lanes and sidewalks on both sides |  | CST, CEI | CST, CEI, LS
3 | 205083 | Hickory Bridge Replacements | Age | 0 | 8188912 | 0 | 4770011 | 0 | 0 | 0 | 4770011 | 99351742 | 112310665 | ST | Tom Marquardt
|  | Project combines New Pass, Little Carlos and Big Hickory bridge, including demolition and disposal of the olf bridges. | Condition of bridge (Bridge Health Index) |  | PD&E Study |  | DES |  |  |  |  | CST/CEI |  | FDOT | tmarquardt@leegov.com
5 | 200637 | Lee Blvd Traffic Signals | Improve safety | 752930 | 682200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1435130 | GT | Mike Padgett
|  |  | Intersections meet signal | DES/CST | CST | [9 empty] | mpadgett@leegov.com
|  | Lee Boulevard/Lee Street Traffic Signal | warrants and
|  | Lee Boulevard/Joan Avenue Traffic Signal | almost meet
crash warrants
2,4 | 240613 | Ortiz 4L/Colonial-MLK | Parallel reliever to I-75, | 1885450 | 33368279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35253729 | IF23 | Rob Phelan
|  | Widening of Ortiz from Colonial Blvd to Martin Luther King Blvd | access to jail and EMS, | ROW/DES | DES/MIT | [8 empty] | GT | rphelan@leegov.com
|  |  | LOS per Concurrenty Rpt, | [10 empty] | FDOT
|  |  | City tie-in of Hanson St.ext | [10 empty] | Debt
4,5 | 204072 | Ortiz 4L/MLK-Luckett/Luckett-I75 | Parallel relief to I-75 | 9251258 | 4796696 | 0 | 0 | 0 | 0 | 0 | 0 | 43635913 | 57683867 | IF23 | Rob Phelan
|  | Widening of Ortiz from Martin Luther Kind Blvd to Lucket Rd, inclduing the widening of | improve area circulation | DES/ROW | ROW/DES | [6 empty] | LS |  | GT | rphelan@leegov.com
|  | Luckett Rd | improve LOS
NM - Essential
ALL | 206759 | Signal System ATMS Upgrade | Maximizes efficient use | 7504288 | 1637045 | 750000 | 750000 | 750000 | 750000 | 750000 | 3750000 | 0 | 12891333 | GT | Mike Padgett
|  | Upgrade of existing traffic signal system | of existing capacity | CST | CST | CST | CST | CST | CST | CST |  |  |  |  | mpadgett@leegov.com
2 | 204053 | Three Oaks Parkway Extension North | Extends major arterial, | 12842258 | 87965148 | 6311828 | 46687971 | 0 | 0 | 0 | 52999799 | 0 | 153807205 | IF23,24 | Vince Miller
|  | Extension of Three Oaks from current ending point through Daniels Pkwy, includes | parallel reliever to I-75 | DES/ROW | DES/ROW | CST/CEI | CST/CEI | [6 empty] | GIF/GT | vmiller@leegov.com
|  | major updates to the Daniels Pkwy intersection, constructed in three phases | NM - Essential | Project Mgmt | CST/CEI | [8 empty] | Debt
GIF
1,2,3 | 205818 | Toll Interoperability | Age of equipment, rapid | 656461 | 476588 | 150000 | 150000 | 150000 | 150000 | 150000 | 750000 | 0 | 1883049 | ST | Sue Drotleff
|  | Upgrade to hardware and software to handle new transponder protocols | technology changes | CST | CST | CST | CST | CST | CST | CST |  |  |  |  | sdrotleff@leegov.com
NM - Core Critical
1,2,3 | 200615 | Toll System Replacement | Age of equipment, rapid | 0 | 13250000 | 0 | 0 | 0 |  | 0 | 0 | 0 | 13250000 | ST | Sue Drotleff
|  | Replace hardware and software for toll lanes, computers and revenue collection | technology changes |  | DES | [9 empty] | sdrotleff@leegov.com
|  | software | NM - Core Critical
KEY (PHASES): |  | PD&E = Project Development & Environmental Study; DES = Design; ROW = Right-of-Way Acquisition; CST = Construction; CEI = Construction Engineering Inspection;
MIT = Mitigation
KEY (FUNDS): |  | IF = Road Impact Fees w/District; GT = Local Option Gas Taxes; FDOT = Florida Dept. of Transportation; GIF = Growth Increment Funding, ST = Surplus Tolls